## Housing CIP and Other Projects
Capital Improvement Plan for Housing Initiatives
Project Name | Total Cost* [Estimated] | Year of Estimate | Estimate / Financials Source | Current State | High-Level Project Description | Anticipated Project Impact | Approximate Project Timeline
Old Henderonsville Hwy and Azalea Ave Sewer Extension
Non-Construction (Engineering & Permitting) | 95000 | 2024 | Summit Engineering | Proposed | Sewer extension along Old Hendersonville Hwy and Azalea Ave as a first phase of the larger Azalea / Rhododendron neighborhood sewer extension project (includes pump station to serve the entire area) and also brings sewer to a City-owned property for the development of 40-50 new affordable rental units. Project will improve public health/quality of life by replacing failing septic systems, reduce contamination of the French Broad River, preserve existing housing units, and allow for the development of new housing (affordable and market-rate) on vacant properties near the new sewer infrastructure. | 40-50 new affordable rental units on City-owned Azalea site and sewer extension to 28 other primarily residential parcels | 18 months (design, construction, connection to existing housing)
Construction | 1744231 | 2024 | Summit Engineering | Proposed
Azalea / Rhododendron Neighborhood Sewer Extension**
Non-Construction (Engineering & Permitting) | 567500 | 2025 | Summit Engineering | Proposed | Sewer extension to the entire Azalea / Rhododendron neighborhood sewer extension project that also brings sewer to a City-owned property for the development of 40-50 new affordable rental units. Project will improve public health/quality of life by replacing failing septic systems, reduce contamination of the French Broad River, preserve existing housing units, and allow for the development of new housing (affordable and market-rate) on vacant properties throughout the neighborhood. | 40-50 new affordable rental units on City-owned Azalea site and sewer extension to 125 other primarily residential parcels | 2 years (design, easement acquisition, construction, and connections to existing housing)
Construction | 4475735 | 2025 | Summit Engineering | Proposed
Habitat for Humanity Woodland Terrace Sewer Extension
Non-Construction (Engineering & Permitting) | 113000 | 2024 | Summit Engineering | Proposed | Sewer extention to a 7.8 acre parcel on Woodland Terrace that is owned by Transylvania Habitat for Humanity. Development is anticipated to include up to 47 new affordable units. | Up to 47 new affordable units | 8 months (infrastructure only)
Construction | 523000 | 2024 | Summit Engineering | Proposed
Housing Assistance Corporation Cashiers Valley Road Project
Sewer Extension along Cashier's Valley Road | 40000 | 2025 | City Public Works (materials and staff time) | Committed | Infrastructure to serve 10-20 units on Cashiers Valley Rd developed by Housing Assistance Corporation. In July 2025, City entered into development agreement with HAC to convey property and extend infrastructure along Cashier's Valley Road in exchange for the development of 10-20 affordable for-sale homes. | 10-20 new affordable for-sale units | 2 years (entire project - infrastructure and units)
Road Construction within Parcel | 332900 | 2025 | WGLA Engineering | Proposed
Sewer Extension within Parcel | 244500 | 2025 | WGLA Engineering | Proposed
Water Extension within Parcel | 163950 | 2025 | WGLA Engineering | Proposed
Fairhaven Meadows
Sewer Extension and Hydrants | 387119 | - | Infrastructure portion of City's $1,169,000 loan | Committed | In March 2025, City loaned developer Commonwealth Co. $1,169,000 in gap financing for the 42-unit affordable housing development on Asheville Hwy. Project was first new construction LIHTC project in the County in 13 years. | 42 new affordable rental units | Under construction, estimated completion Oct 2026
Other Housing-Related Expenditures (Not Capital)
Project Name | Total Cost* [Estimated] | Year of Estimate |  | Current State | High-Level Project Description | Anticipated Project Impact | Approximate Project Timeline
Affordable Housing Assessment / Azalea Avenue Site
DFI Professional Services | 90000 | - | Paid through City's Housing Trust Fund | Complete | In 2023, the City contracted DFI to conduct a housing needs assessment, identify potential sites for an affordable housing development, conduct a site-suitability analysis, and assist the City in soliciting a developer to construct the project. This included geotechnical, architectural, and financial feasibility assessments. In April 2025, the City purchased 3.8 acres on Azalea Ave and Old Hendersonville Hwy for the creation of 40-50 new affordable rental units. DFI determined that even with a LIHTC award the funding gap would be around $700,000. Sewer is REQUIRED before pursuing LIHTC funding. | 40-50 new affordable rental units | Developer selected and agreement executed in 2026, LIHTC application 2027, construction beginning 2028 or early 2029
Property Acquisition | 1100000 | - | Negotiated purchase price based on appraised value | Committed
Geotechnical Assessment | 10540 | - | Paid through City's Housing Trust Fund | Complete
Architectural Assessment | 30000 | - | Paid through City's Housing Trust Fund | Complete
Developer Gap Financing | 700000 | 2025 | DFI Analysis | Proposed
Fairhaven Meadows
Other Gap Financing | 781881 | - | Non-infrastructure portion of City's $1,169,000 loan | Committed | In March 2025, City loaned developer Commonwealth Co. $1,169,000 in gap financing for the 42-unit affordable housing development on Asheville Hwy. Project was first new construction LIHTC project in the County in 13 years. | 42 new affordable rental units | Under construction, estimated completion Oct 2026
Housing Assistance Corporation Cashiers Valley Road Project
Property Conveyance | 630000 | - | Property appraised at $630,000; conveyed at no cost | Complete | Infrastructure to serve 10-20 units on Cashiers Valley Rd developed by Housing Assistance Corporation. In July 2025, City entered into development agreement with HAC to convey property and extend infrastructure along Cashier's Valley Road in exchange for the development of 10-20 affordable for-sale homes. | 10-20 new affordable for-sale units | 2 years (entire project - infrastructure and units)
Preservation Programs
Property Tax Relief Programs | TBD | - | - | Proposed | Program to provide property tax relief for low-income homeowners. Proposed project, currently unfunded. | TBD | TBD
Preservation Programs | TBD | - | - | Proposed | Program to support low-income homeowners in repairing and maintaining their homes. Intended to coincide with the Azalea / Rhododendron neighborhood sewer extension project to ensure existing residents are able to remain in the neighborhood. Proposed project, currently unfunded. | TBD | TBD
*None of these figures account for inflation, increasing cost of materials, interest payments on loan amounts, etc.
**The neighborhood extension cost estimate received by Summit Engineering includes the Old Hendersonville Hwy main trunkline and Pump Station. If the funding for sewer extension to the City-owned property on Azalea is funded separately, this estimate will be reduced by approximately $1.8 million. Exact costs would need to be prepared as a separate estimate.